## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | LangChain and all required dependencies (FastAPI, Pydantic v2, provider SDKs, pytest) configured with a centralized config hub, so that every agent has a consistent, reliable environment to run in. | MUST HAVE | None | SHANKAR M | 3- Completed
Sprint 1 | Sprint 1 | US-02 | resilient multi-provider LLM gateway with automatic fallback, so that each BFSI workflow keeps functioning even if an upstream LLM provider is rate-limited or unavailable. | MUST HAVE | US-01 | SHANKAR M | 3- Completed
Sprint 1 | Sprint 1 | US-03 | standardized Abstract Base Agent with built-in telemetry and isolated tool invocation, so that every specialized agent shares consistent logging, latency tracking, and failure handling. | MUST HAVE | US-01 | SHANKAR M | 3- Completed
Sprint 1 | Sprint 1 | US-04 | IntakeExtractionAgent and CreditRiskAnalystAgent, so that borrower documents are parsed and DTI/LTV/VaR risk metrics are computed automatically. | MUST HAVE | US-03 | SHANKAR M | 3- Completed
Sprint 1 | Sprint 1 | US-05 | RegulatoryComplianceAgent, so that every decision is automatically checked against OCC, FinCEN, OFAC, and Basel III rules. | MUST HAVE | US-03 | SHANKAR M | 3- Completed
Sprint 1 | Sprint 1 | US-06 | DecisionApproverAgent with HITL escalation, so that final terms are issued automatically for clear cases and routed to a human for borderline ones. | MUST HAVE | US-04, US-05 | SHANKAR M | 3- Completed
Sprint 1 | Sprint 1 | US-07 | role-conditioned prompt templates with enforced JSON schemas and a shared blackboard memory, so that agents exchange state reliably without hallucinated output structures. | MUST HAVE | US-03 | SHANKAR M | 3- Completed
Sprint 1 | Sprint 1 | US-08 | state-machine orchestrator that streams agent thoughts over WebSockets and auto-queues borderline cases for HITL review. | MUST HAVE | US-07 | SHANKAR M | 3- Completed
Sprint 1 | Sprint 1 | US-09 | visual dashboard (workflow forms, agent topology graph, thought terminal, decision card, HITL queue, knowledge explorer) so that I can exercise all 4 workflows without writing raw JSON. | SHOULD HAVE | US-08 | SHANKAR M | 3- Completed
Sprint 1 | Sprint 1 | US-10 | automated pytest integration suite covering all 4 workflows and HITL/policy retrieval, so that regressions are caught before release. | MUST HAVE | US-08 | SHANKAR M | 3- Completed
Sprint 2 | Sprint 2 | US-11 | custom tool connectors for Core Banking, Credit Bureau, OFAC/AML and the Policy Vector DB, so that agents can reach real enterprise systems and data sources. | MUST HAVE | US-01, US-02 | SHANKAR M | 3- Completed
Sprint 2 | Sprint 2 | US-12 | agents to intelligently choose the correct tool for each situation, so that they don't call irrelevant or duplicate tools. | MUST HAVE | US-11 | SHANKAR M | 3- Completed
Sprint 2 | Sprint 2 | US-13 | monitoring, structured logging, and validation around every tool call, so that failures are visible and don't silently corrupt a decision. | MUST HAVE | US-11 | SHANKAR M | 3- Completed
Sprint 2 | Sprint 2 | US-14 | automated tests for tool invocation workflows, including simulated exceptions, so that tool failures are proven to be handled safely. | MUST HAVE | US-13 | SHANKAR M | 3- Completed
Sprint 2 | Sprint 2 | US-15 | end-to-end validation that action execution is accurate across all 4 workflows, so that tool-driven decisions can be trusted. | SHOULD HAVE | US-14 | SHANKAR M | 3- Completed
Sprint 3 | Sprint 3 | US-16 | each of the 5 specialized agents (Intake, Document/Compliance, Credit Risk, Decision, Planning/Orchestrator) defined with clear business roles and responsibilities, so the system mirrors how a real underwriting team is organized. | MUST HAVE | US-01 - US-10 | SHANKAR M | 3- Completed
Sprint 3 | Sprint 3 | US-17 | decision graph (decision_graph.py) that computes a dependency DAG and dynamically routes execution between agents, so agents coordinate correctly for each application type. | MUST HAVE | US-16 | SHANKAR M | 3- Completed
Sprint 3 | Sprint 3 | US-18 | short-term workflow state (multi_agent_engine.py) that accumulates documents, customer data, and execution trace, so agents share context within one application's run. | MUST HAVE | US-16 | SHANKAR M | 3- Completed
Sprint 3 | Sprint 3 | US-19 | long-term semantic knowledge base (vector_store.py) with cosine-similarity search over KYC/AML/fraud policies, so agents can retrieve the right legal context dynamically. | MUST HAVE | US-11 | SHANKAR M | 3- Completed
Sprint 3 | Sprint 3 | US-20 | validate full collaborative workflow execution end-to-end (Intake to Decision), so multi-agent coordination is proven correct and auditable before Module 4. | MUST HAVE | US-17, US-18, US-19 | SHANKAR M | 3- Completed
Sprint 4 | Sprint 4 | US-21 | complex workflow orchestration (conditional branching, parallel agent execution, retry/backoff) in decision_graph.py, so the platform handles real-world branching scenarios, not just a linear pipeline. | MUST HAVE | US-17 | SHANKAR M | 3- Completed
Sprint 4 | Sprint 4 | US-22 | complete REST + SSE API layer (submit, status, history, live streaming), so external banking systems can integrate with the engine. | MUST HAVE | US-21 | SHANKAR M | 3- Completed
Sprint 4 | Sprint 4 | US-23 | monitoring dashboard showing live workflow status, agent health, latency, and error rates, so the platform is observable in production. | MUST HAVE | US-22 | SHANKAR M | 3- Completed
Sprint 4 | Sprint 4 | US-24 | backend deployed to Render and the frontend deployed to Vercel with CI/CD, so the platform runs reliably outside a local dev environment. | MUST HAVE | US-22, US-23 | SHANKAR M | 3- Completed
Sprint 4 | Sprint 4 | US-25 | load/performance testing and optimization conducted on the full pipeline, so the platform meets production SLAs before release. | MUST HAVE | US-24 | SHANKAR M | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 308 | 32 | 46 | 22 | 33.3 | 33.4 | 38.7 | 22.7 | 18 | 36 | 32.7 | 37.4 | 32 | 27.4 | 5
SPRINT 1 BACKLOG
US-01 | T-01 | Set up pyproject.toml, Python venv & core dependency manifest | 2026-08-18 | 2026-08-18 | SHANKAR M | Build | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Configure unified config hub (backend/config.py, backend/.env) incl. QM DTI / OFAC / Basel III thresholds | 2026-08-18 | 2026-08-18 | SHANKAR M | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-03 | Implement multi-provider LLM gateway with automatic failover (backend/llm/client.py) | 2026-08-19 | 2026-08-20 | SHANKAR M | Coding | 3- Completed | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-04 | Build Abstract Base Agent: telemetry, confidence scoring, isolated tool invocation (base_agent.py) | 2026-08-19 | 2026-08-20 | SHANKAR M | Coding | 3- Completed | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-05 | Implement IntakeExtractionAgent - OCR & payroll verification tools | 2026-08-21 | 2026-08-22 | SHANKAR M | Coding | 3- Completed | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-06 | Implement CreditRiskAnalystAgent - DTI/LTV/VaR calculations | 2026-08-22 | 2026-08-23 | SHANKAR M | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-07 | Implement RegulatoryComplianceAgent - OCC/FinCEN/OFAC/Basel III checks | 2026-08-23 | 2026-08-24 | SHANKAR M | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-08 | Implement DecisionApproverAgent - arbitration, pricing engine, HITL gating | 2026-08-24 | 2026-08-25 | SHANKAR M | Coding | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-09 | Design role-conditioned system prompts & enforce deterministic JSON schemas | 2026-08-25 | 2026-08-26 | SHANKAR M | Design | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-10 | Build shared blackboard memory manager & persistent audit_db.json ledger | 2026-08-26 | 2026-08-26 | SHANKAR M | Coding | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | T-11 | Build state-machine orchestrator with 4-phase pipeline & WebSocket thought streaming | 2026-08-26 | 2026-08-27 | SHANKAR M | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
US-09 | T-12 | Build React dashboard: WorkflowStudio, AgentGraphVisualizer, ExecutionConsole, DecisionCard, HitlQueue, KnowledgeBaseExplorer | 2026-08-27 | 2026-08-29 | SHANKAR M | Coding | 3- Completed | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 10.7 | 0 | 0 | 0
US-10 | T-13 | Write & execute 6-suite automated pytest integration test suite | 2026-08-30 | 2026-08-31 | SHANKAR M | Integration Test | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
SPRINT 2 BACKLOG
US-11 | T-14 | Build tool connectors: Core Banking & Credit Bureau APIs (Week 3) | 2026-09-01 | 2026-09-03 | SHANKAR M | Coding | 3- Completed | 12 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-15 | Build tool connectors: OFAC/AML screening & Policy Vector DB (Week 3) | 2026-09-03 | 2026-09-05 | SHANKAR M | Coding | 3- Completed | 8 | 0 | 0 | 8 | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-16 | Implement intelligent tool-selection logic in base agent (Week 3) | 2026-09-05 | 2026-09-07 | SHANKAR M | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 10 | 6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-17 | Add monitoring & structured logging for every tool call (Week 4) | 2026-09-08 | 2026-09-09 | SHANKAR M | Coding | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-18 | Add validation & error-handling wrapper around tool invocation (Week 4) | 2026-09-09 | 2026-09-10 | SHANKAR M | Coding | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
US-14 | T-19 | Write tests for tool invocation workflows & simulated exceptions (Week 4) | 2026-09-11 | 2026-09-12 | SHANKAR M | Unit Test | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
US-15 | T-20 | Validate end-to-end action execution accuracy across all 4 workflows (Week 4) | 2026-09-12 | 2026-09-14 | SHANKAR M | System Test | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6.7 | 0
SPRINT 3 BACKLOG
US-16 | T-21 | Define & formalize the 5 agent business roles (Intake, Document/Compliance, Credit Risk, Decision, Planning/Orchestrator) (Week 5) | 2026-09-15 | 2026-09-16 | SHANKAR M | Design | 3- Completed | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-22 | Build decision_graph.py — dependency DAG computation & dynamic execution routing (Week 5) | 2026-09-16 | 2026-09-18 | SHANKAR M | Coding | 3- Completed | 12 | 0 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-23 | Build multi_agent_engine.py — short-term workflow state (documents, customer data, execution trace) (Week 5) | 2026-09-18 | 2026-09-20 | SHANKAR M | Coding | 3- Completed | 10 | 0 | 0 | 0 | 10 | 6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-24 | Build vector_store.py — cosine-similarity semantic search over policy documents (Week 5-6) | 2026-09-20 | 2026-09-22 | SHANKAR M | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-25 | Load & index KYC/AML/fraud-protocol documents into vector_store (Week 6) | 2026-09-22 | 2026-09-23 | SHANKAR M | Coding | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-26 | Implement agent-to-agent communication/coordination mechanism via shared state (Week 6) | 2026-09-23 | 2026-09-25 | SHANKAR M | Coding | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6.7 | 0 | 0 | 0 | 0
US-20 | T-27 | Validate collaborative workflow execution end-to-end + audit-trail logging of agent reasoning (Week 6) | 2026-09-25 | 2026-09-28 | SHANKAR M | System Test | 3- Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 9 | 6 | 0
SPRINT 4 BACKLOG
US-21 | T-28 | Implement conditional branching & parallel agent execution in decision_graph.py (Week 7) | 2026-09-29 | 2026-10-01 | SHANKAR M | Coding | 3- Completed | 12 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-21 | T-29 | Add retry/backoff logic for failed agent steps within a workflow (Week 7) | 2026-10-01 | 2026-10-02 | SHANKAR M | Coding | 3- Completed | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-22 | T-30 | Build full REST API endpoints (submit/status/history) + SSE streaming endpoint (Week 7) | 2026-10-02 | 2026-10-04 | SHANKAR M | Coding | 3- Completed | 10 | 0 | 0 | 0 | 10 | 6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-23 | T-31 | Build monitoring dashboard — live workflow status, agent health, latency/error charts (Week 7-8) | 2026-10-04 | 2026-10-06 | SHANKAR M | Coding | 3- Completed | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-24 | T-32 | Containerize backend & frontend (Docker) and set up CI/CD pipeline (Week 8) | 2026-10-07 | 2026-10-08 | SHANKAR M | Coding | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0
US-24 | T-33 | Deploy backend to Render and frontend to Vercel (staging) (Week 8) | 2026-10-08 | 2026-10-10 | SHANKAR M | Build | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6.7 | 3 | 0 | 0
US-25 | T-34 | Conduct load/performance testing & optimize pipeline bottlenecks (Week 8) | 2026-10-10 | 2026-10-12 | SHANKAR M | System Test | 3- Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6.7 | 5
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 (18-Aug-2026) | None | Kicked off environment setup; agreed on dependency manifest.
Sprint 1 | Day 2 (19-Aug-2026) | Provider API key for Groq Cloud was delayed | Used temporary sandbox key to unblock LLM gateway work.
Sprint 1 | Day 4 (21-Aug-2026) | Fallback logic for LLM gateway not triggering on 429 errors (Defect #1) | Root-caused missing exception handler; fix scheduled for Day 4.
Sprint 1 | Day 6 (23-Aug-2026) | IntakeExtractionAgent returning malformed JSON on low-confidence OCR (Defect #2) | Added strict schema sanitization in base agent layer.
Sprint 1 | Day 7 (24-Aug-2026) | DTI boundary miscalculation near 43% QM cap (Defect #3) | Corrected formula and added boundary regression tests.
Sprint 1 | Day 9 (26-Aug-2026) | WebSocket thought stream dropping on reconnect (Defect #5) | Implemented auto-reconnect with session replay.
Sprint 1 | Day 11 (28-Aug-2026) | Dashboard build slower than expected due to 6-component scope | Reprioritized to finish WorkflowStudio & DecisionCard first.
Sprint 1 | Day 13 (30-Aug-2026) | None | Started full pytest integration suite run across all 4 workflows.
Sprint 1 | Day 14 (31-Aug-2026) | None | All 6 integration test suites passing; milestone marked complete.
Sprint 2 | Day 8 (08-Sep-2026) | None | Started structured logging/monitoring wrapper around all tool calls.
Sprint 2 | Day 9 (09-Sep-2026) | Tool-selection logic called credit_bureau twice in one run (Defect #9) | Added per-session tool-result caching to avoid duplicate calls.
Sprint 2 | Day 10 (10-Sep-2026) | OFAC/AML connector silently passed on API timeout (Defect #10) | Added explicit timeout handling; unverified checks now route to HITL.
Sprint 2 | Day 12 (12-Sep-2026) | Simulated 500-error test case for Policy Vector DB connector not yet covered (Defect #11, Open) | Test case scheduled; exception-handling coverage in progress.
Sprint 2 | Day 14 (14-Sep-2026) | None | End-to-end action execution validation across all 4 workflows underway.
Sprint 3 | Day 15 (15-Sep-2026) | None | Kicked off Module 3; began formalizing the 5 agent roles and responsibilities.
Sprint 3 | Day 17 (17-Sep-2026) | None | Started decision_graph.py — dependency DAG computation between agents.
Sprint 3 | Day 20 (20-Sep-2026) | None | Began vector_store.py semantic knowledge base with cosine-similarity search.
Sprint 3 | Day 22 (22-Sep-2026) | None | Loaded KYC/AML/fraud-protocol documents into the vector store.
Sprint 3 | Day 23 (23-Sep-2026) | vector_store returning duplicate near-identical policy chunks (Defect #12) | Added de-duplication on top-k retrieval results.
Sprint 3 | Day 24 (24-Sep-2026) | Dependency DAG could deadlock on circular agent dependencies (Defect #13) | Added a DAG-cycle validation check at workflow startup.
Sprint 3 | Day 25 (25-Sep-2026) | Execution trace timestamps occasionally out of order (Defect #14, Open) | Root-caused an async write race in the trace logger; fix in progress.
Sprint 3 | Day 28 (28-Sep-2026) | None | Running full end-to-end collaborative workflow validation (Intake → Decision) ahead of Module 4.
Sprint 4 | Day 29 (29-Sep-2026) | None | Kicked off Module 4; started conditional branching & parallel execution in decision_graph.py.
Sprint 4 | Day 30 (30-Sep-2026) | None | Added retry/backoff logic for transient agent failures.
Sprint 4 | Day 32 (02-Oct-2026) | None | Built out REST submit/status/history endpoints and the SSE streaming endpoint.
Sprint 4 | Day 34 (04-Oct-2026) | None | Started the monitoring dashboard — live workflow status and agent health.
Sprint 4 | Day 37 (07-Oct-2026) | Race condition on parallel agent writes to shared state (Defect #15) | Added per-key write lock; began containerizing backend & frontend.
Sprint 4 | Day 38 (08-Oct-2026) | SSE stream silently dropping after ~5 min on cloud deploy (Defect #16) | Added SSE keep-alive heartbeat; fixed in staging.
Sprint 4 | Day 40 (10-Oct-2026) | MongoDB connection pool exhausted under 50 concurrent workflows (Defect #17, Open) | Increasing MongoDB connection pool size and adding request queuing; continuing backend deploy to Render and frontend deploy to Vercel.
Sprint 4 | Day 42 (12-Oct-2026) | None | Running load/performance tests and tuning bottlenecks ahead of Milestone 4 close.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-08-18 | 2026-08-31 | SHANKAR M | Write unit tests alongside each agent as it is built, not only at the end. | Hardcoding thresholds (DTI, OFAC, Basel III) inside the code instead of reading them from config. | Using the shared blackboard pattern for passing state between agents - it kept hand-offs clean. | Adopted config-driven thresholds project-wide and added a fallback test for every LLM provider.
2 | Sprint 2 | 2026-09-01 | 2026-09-14 | SHANKAR M | Add timeout and exception handling to every external tool connector from day one. | Letting a failed tool call pass silently (the OFAC timeout returned an empty result as if the check passed). | Structured logging of every tool call and per-session caching to avoid duplicate calls. | Failed or timed-out checks are now marked 'unverified' and routed to human review; simulated 500-error tests added.
3 | Sprint 3 | 2026-09-15 | 2026-09-28 | SHANKAR M | Validate the agent dependency graph (cycle check) at workflow startup. | Writing the execution trace with unordered async writes, which broke the audit timeline order. | Keeping short-term state (workflow engine) and long-term memory (vector store) as separate, individually tested layers. | Added DAG-cycle validation, an ordered trace-write queue, and de-duplication of vector-search results.
4 | Sprint 4 | 2026-09-29 | 2026-10-12 | SHANKAR M | Test on the deployed setup (Render backend, Vercel frontend) early, not only on localhost. | Assuming local behaviour equals cloud behaviour - the SSE stream drop only appeared on Render. | Locking shared state for parallel agents and running load tests before release. | Added SSE keep-alive heartbeat; tuning the MongoDB connection pool after the 50-workflow load test.
5
6
7