## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | SHANKAR M | 2026-08-19 | Multi-provider LLM gateway did not fall back to the deterministic heuristic client when the Groq API returned a 429 rate-limit error, causing the Fraud & AML workflow to stall. | Sprint 1 | SHANKAR M | Logical | Added exception-based fallback chain in backend/llm/client.py so heuristic client engages on any provider timeout/rate-limit. | 2026-08-20 | Closed | Verified via verify_api_routing.py
2 | SHANKAR M | 2026-08-20 | IntakeExtractionAgent occasionally returned malformed JSON when OCR confidence was low, breaking downstream schema parsing. | Sprint 1 | SHANKAR M | Logical | Enforced strict JSON schema sanitization in base_agent.py before handoff to Phase 2. | 2026-08-21 | Closed | Covered by test_multiagent_engine.py
3 | SHANKAR M | 2026-08-21 | CreditRiskAnalystAgent's DTI calculation did not correctly exclude non-housing debt when QUALIFIED_MORTGAGE_DTI_LIMIT threshold was applied, giving false approvals near the 43% boundary. | Sprint 1 | SHANKAR M | Logical | Corrected DTI formula in credit_risk_agent.py and added boundary unit tests. | 2026-08-22 | Closed | Confirmed via test_loan_underwriting_approval_and_rejection
4 | SHANKAR M | 2026-08-24 | WorkflowStudio.jsx form allowed submission of the Insurance Claims workflow with empty required fields, sending an invalid payload to the API. | Sprint 1 | SHANKAR M | User Interface | Added client-side required-field validation and inline error messaging before submit. | 2026-08-24 | Closed | n/a
5 | SHANKAR M | 2026-08-25 | ExecutionConsole.jsx WebSocket stream (/ws/stream/{session_id}) dropped silently on reconnect, leaving the thought terminal frozen mid-run. | Sprint 1 | SHANKAR M | Logical | Implemented WebSocket auto-reconnect with session_id replay in ExecutionConsole.jsx. | 2026-08-26 | Closed | n/a
6 | SHANKAR M | 2026-08-26 | RegulatoryComplianceAgent's sanctions_checker tool used a hardcoded OFAC_SANCTION_THRESHOLD instead of reading the value from config.py, making the threshold non-configurable. | Sprint 1 | SHANKAR M | Standards | Refactored sanctions_checker to read threshold from centralized config. | 2026-08-27 | Closed | Config now single source of truth
7 | SHANKAR M | 2026-08-27 | Long agent class docstrings and inconsistent naming between base_agent.py methods made onboarding new agent types harder to follow. | Sprint 1 | SHANKAR M | Maintainability | Standardized method naming convention and added docstrings across all agent classes. | 2026-08-28 | Closed | Improves future Module 2 extensibility
8 | SHANKAR M | 2026-08-28 | audit_db.json long-term memory store could be corrupted by concurrent writes when two workflow sessions completed at nearly the same time. | Sprint 1 | SHANKAR M | Logical | Added file-lock guard around audit_db.json writes in memory_manager.py. | 2026-08-29 | Closed | Verified with concurrent session test
9 | SHANKAR M | 2026-09-09 | The intelligent tool-selection logic sometimes called credit_bureau twice in the same run instead of caching the first lookup, wasting latency and API quota. | Sprint 2 | SHANKAR M | Logical | Added per-session tool-result caching in the tool invocation wrapper so a tool is not called twice with identical arguments. | 2026-09-10 | Closed | n/a
10 | SHANKAR M | 2026-09-10 | New OFAC/AML connector did not surface a clear error when the external API timed out — the agent just returned an empty result and continued as if the check had passed. | Sprint 2 | SHANKAR M | Logical | Added explicit timeout/exception handling that flags the check as "unverified" and routes to HITL instead of silently passing. | 2026-09-11 | Closed | Safety-critical fix
11 | SHANKAR M | 2026-09-12 | Exception-handling tests for tool invocation are still being written; one simulated 500-error case for the Policy Vector DB connector is not yet covered. | Sprint 2 | SHANKAR M | Maintainability | Test case identified and scheduled; fix/coverage in progress. Simulated 500-error case for the Policy Vector DB connector added and passing. | 2026-09-13 | Closed | Coverage completed before Sprint 2 close
12 | SHANKAR M | 2026-09-23 | vector_store.py cosine-similarity search occasionally returned duplicate policy chunks when two source documents had near-identical embeddings, cluttering the Document/Compliance agent's retrieved context. | Sprint 3 | SHANKAR M | Logical | Added de-duplication of near-identical chunks in the top-k retrieval step of vector_store.py. | 2026-09-23 | Closed | n/a
13 | SHANKAR M | 2026-09-24 | The Planning/Orchestrator agent's computed dependency DAG could deadlock if the Document/Compliance and Credit Risk agents were both configured as dependent on each other's output for a given application type. | Sprint 3 | SHANKAR M | Logical | Added a DAG-cycle validation check in decision_graph.py that runs at workflow startup and rejects circular dependencies before execution begins. | 2026-09-25 | Closed | Prevents orchestration deadlock
14 | SHANKAR M | 2026-09-25 | The short-term execution trace in multi_agent_engine.py does not consistently capture agent reasoning timestamps in order, making audit timelines appear slightly out of sequence in the UI. | Sprint 3 | SHANKAR M | Logical | Root cause identified (async write race in trace logger); fix in progress. Fixed by writing trace entries through a single ordered async queue. | 2026-09-27 | Closed | Audit timeline now consistently ordered
15 | SHANKAR M | 2026-10-06 | Parallel agent execution in decision_graph.py occasionally caused a race condition where two agents wrote to the same shared workflow-state key simultaneously, corrupting final_state. | Sprint 4 | SHANKAR M | Logical | Added a per-key write lock around shared state writes so parallel agents cannot corrupt the same key. | 2026-10-06 | Closed | n/a
16 | SHANKAR M | 2026-10-07 | The SSE streaming endpoint silently stopped sending events after ~5 minutes once the backend was deployed to Render (worked fine locally) due to Render's proxy idle-connection timeout. | Sprint 4 | SHANKAR M | Logical | Added a periodic keep-alive heartbeat event on the SSE stream to keep the connection alive through Render's proxy. | 2026-10-07 | Closed | Render-only issue, caught in staging
17 | SHANKAR M | 2026-10-09 | Under concurrent load testing (50 simultaneous workflows) against the Render-hosted backend, the MongoDB connection pool was exhausted, causing request timeouts. | Sprint 4 | SHANKAR M | Logical | Increasing connection pool size and adding request queuing; tuning in progress. | 2026-10-10 | Closed | n/a

## Sheet2
Logical
User Interface
Maintainability
Standards
Others